Purpose: Establish strategies, tactics, and resource needs to meet the Incident

Objectives for the next Operational Period

When: After the Incident Briefing, and after Sections have met (about 15 minutes) to

discuss their response priorities

Attendees: Incident Commander, Command Staff, General Staff.  Other attendees may

be assigned by the Incident Commander.

Facilitated by: Planning Section Chief or Incident Commander

Length of Time: short; no longer than 10-15 minutes

Prior to the meeting

- The Incident Commander should complete HICS Form 201 Incident Briefing

- The Incident Commander should request each Section Chief to:

  - Meet with their Section staff to discuss Section-specific Incident Objectives, strategies, tactics, and resources assigned and resource needs for the next operational period

  - Complete HICS 204 Assignment List  to be presented at the incident action planning meeting

  - HICS 204 can be used to represent an entire Section or a Branch within a Section

- The Safety Officer should begin HICS 215A Incident Action Plan Safety Analysis

After the meeting

- The Safety Officer should finalize HICS 215A Incident Action Plan Safety Analysis based on reports from the incident action planning meeting, and submit to the Planning Section

- The Planning Section should:

  - Complete HICS 202 Incident Objectives by identifying the Incident Objectives from the Incident Commander’s incident briefing, and additional information as identified during the incident action planning meeting

  - Complete HICS 203 Organization Assignment List based on each Section’s HICS 204

  - Compile the HICS Forms (201, 202, 203, 204, and 215A) and any other supplemental information such as maps into one Incident Action Plan for the Operational Period

  - Complete the HICS 200 Incident Action Plan Cover Sheet

  - Submit the completed Incident Action Plan to the Incident Commander for approval

  - Disseminate the approved Incident Action Plan so that it can be used in Operational  Period Briefings for supervisors to inform staff of the plan for the next operational period

Agenda

- Situation briefing (from HICS Form 201 Incident Briefing) - may be provided by the Incident Commander or the Planning Chief

- Reports from General Staff (Section/Branch Incident Objectives, strategies, tactics, and resources assigned/needed to meet the objectives)

  - Operations Chief

  - Logistics Chief

  - Finance/Administration Chief

  - Planning Chief

- Reports from Command Staff (if there are specific issues to consider)

  - Safety Officer

  - Public Information Officer

  - Liaison Officer

  - Medical/Technical Specialist(s)

- Comments, concerns, questions

- Wrap-Up